## Sheet1
Summary
| Project | Boundary Wall Construction for ACME Chemical Plant | [7 empty] | Created on WorkPack
| Planned Progress | 9 | %
| Actual Progress | 7.9503 | % |  | Schedule Variance | -11.6639 | %
| Earned Value | 22332.2619 | $
| Actual costs | 24596.5714 | $ |  | Cost Variance | -10.1392 | % |  |  | www.workpack.in
| S. No. | Task | Effort (Mandays) | Costs | Value (to be billed) | Scope of Work | Unit | Weightage (Effort Basis) | Weightage (Value Basis) | Actual Work Done | Unit | Actual Effort Spent (Days) | Actual Costs | Task Progress (%)
| 1 | Task1 | 15 | 450 | 500 | 1 | Nos | 2.2091 | 0.178 | 1 | Nos | 17 | 510 | 100 | 0.178 | 500
| 2 | Task2 | 2 | 90 | 100 | 5 | Nos | 0.29455 | 0.0356 | 4 | Nos | 2 | 90 | 80 | 0.02848 | 80
| 3 | Task3 | 35 | 7650 | 8500 | 45 | Cubic M | 5.1546 | 3.026 | 30 | Cubic M | 28 | 6120 | 66.6667 | 2.0173 | 5666.6667
| 4 | Task4 | 42 | 13500 | 15000 | 1200 | Kg | 6.1856 | 5.34 | 500 | Kg | 20 | 6428.5714 | 41.6667 | 2.225 | 6250
| 5 | Task5 | 60 | 22500 | 25000 | 6000 | Lit | 8.8365 | 8.9 | 1000 | Lit | 9 | 3375 | 16.6667 | 1.4833 | 4166.6667
| 6 | Task6 | 15 | 16650 | 18500 | 5000 | Kg | 2.2091 | 6.586 | 500 | Kg | 3 | 3330 | 10 | 0.6586 | 1850
| 7 | Task7 | 100 | 45900 | 51000 | 5000 | Sq. Ft | 14.7275 | 18.1559 | 300 | Sq. Ft | 7 | 3213 | 6 | 1.0894 | 3060
| 8 | Task8 | 10 | 7650 | 8500 | 560 | M | 1.4728 | 3.026 | 50 | M | 2 | 1530 | 8.9286 | 0.27018 | 758.9286
| 9 | Task9 | 150 | 77400 | 86000 | 150 | Cubic M | 22.0913 | 30.6159 |  | Cubic M |  | 0 | 0 | 0 | 0
| 10 | Task10 | 200 | 56700 | 63000 | 3000 | Sq. Ft | 29.4551 | 22.4279 |  | Sq. Ft |  | 0 | 0 | 0 | 0
| 11 | Task11 | 8 | 1080 | 1200 | 120 | M | 1.1782 | 0.4272 |  | M |  | 0 | 0 | 0 | 0
| 12 | Task12 | 10 | 540 | 600 | 450 | Lit | 1.4728 | 0.2136 |  | Lit |  | 0 | 0 | 0 | 0
| 13 | Task13 | 5 | 630 | 700 | 42 | Nos | 0.73638 | 0.2492 |  | Nos |  | 0 | 0 | 0 | 0
| 14 | Task14 | 12 | 720 | 800 | 3000 | Nos | 1.7673 | 0.2848 |  | Nos |  | 0 | 0 | 0 | 0
| 15 | Task15 | 15 | 1350 | 1500 | 500 | Kg | 2.2091 | 0.534 |  | Kg |  | 0 | 0 | 0 | 0
|  | Total | 679 | 252810 | 280900 |  |  | 100 | 100 |  |  | 88 | 24596.5714 | 7.9503 | 7.9503
Note | If you are interested in using an automated version of this spreadsheet to implement the earned value management in your projects, write to us - support@workpack.in
Weightage Factor for individual tasks are calculated based on billing value, as it represents a more realistic picture of how important a task is - compared to efforts taken.
We can arrange for a free consulting session for your project team.